## Summary
Which statement accurately characterizes Strate...
Select the 3 elements of the user voice form of...
SAFe requires Epics to be estimated in order to...
Which pillar of the House of Lean can help us e...
Stretch objectives are technical or functional ...
What SAFe practice best supports capacity-based...
What is the primary role of the SAFe portfolio?
A crosscutting Epic that spans multiple PIs is ...
During the System Demo, it turns out that each ...
When should a crosscutting Enabler be implement...
Which of these Lean-Agile Principles is one of ...
What element of the framework best realizes Pri...
Which of the following is NOT a step in the Por...
Which of the following is an output from Pre- a...
The Program and Value Stream Backlogs are the s...
The goal of the Capability section of the Value...
Which one of the following statements about Ena...
What period of time should the Program and Valu...
What does the program Roadmap do in SAFe?
The Team Backlog contains the Stories that the ...
Which is the most accurate statement about Weig...
What is the goal of Lean?
Business Owners assign business value to the Te...
Who typically holds responsibility for implemen...
Select the statement that best describes the co...
Which statement best describes Architectural Ru...
In an Enterprise with one Solution portfolio an...
During Pre-PI Planning, Solution Management rea...
Value Stream Budget allocation decisions are ma...
Why is Test-First important?
Which SAFe Core Value best supports why teams a...
When is the best time to release software in SAFe?
In what scenario would 4-level SAFe most likely...
What best describes how a large Value Stream re...
A company is struggling to implement Agile. Man...
The analysis state of the Portfolio Kanban syst...
The SAFe Principle “Assume variability; preserv...
A single Agile Release Train can have software,...
What is the most effective way to avoid waterfa...
The importance of this event cannot be overstat...
Feature teams are beneficial because they have ...
What is the recommended way to express a Featur...
What best describes aspects of the team's commi...
During the Inspect & Adapt, teams identified a ...
How would you most simply measure average lead ...
When is Pre-PI Planning needed?
After what event should there be agreement on t...
What role accepts Capabilities?
Which of the following in SAFe is an example of...
What event is of highest importance in SAFe?
At the end of PI Planning, Day 2, it turns out ...
What is the foundation of the SAFe House of Lean?
The SAFe Principles should be implemented in se...
Why do we prioritize with Weighted Shortest Job...

## Detailed
S.No | Question and Choice | Category
1 | Which statement accurately characterizes Strategic Themes?
Strategic Themes represent the key direction for the portfolio, providing a link between Enterprise business strategy and economic decision-making within the portfolio
Strategic Themes are budget allocations for Value Streams
Strategic Themes are a high-level summary of each program’s Vision, updated after every Program Increment
Strategic Themes are large initiatives managed in the Portfolio Kanban that require WSJF prioritization and a lightweight business case
2 | Select the 3 elements of the user voice form of user stories.
User role, activity, business value
User, benefit, action
Benefit, business purpose, risks
User, specification, value
3 | SAFe requires Epics to be estimated in order to forecast
TRUE
FALSE
4 | Which pillar of the House of Lean can help us explain why projects often hinder Enterprise agility?
4 | Respect for people and culture
4 | Innovation
4 | Relentless improvement
4 | Flow
- | - | -
5 | Stretch objectives are technical or functional spikes needed to uncover knowledge or reduce risk in the next PI.
TRUE
FALSE
- | - | -
6 | What SAFe practice best supports capacity-based planning?
Conducting the System Demo at the end of each sprint
Updating the Roadmap before each Release planning meeting
Using common story point estimating across teams
Implementing Test-First code quality practices
- | - | -
7 | What SAFe practice best supports capacity-based planning?
Conducting the System Demo at the end of each sprint
Updating the Roadmap before each Release planning meeting
Using common story point estimating across teams
Implementing Test-First code quality practices
- | - | -
8 | What is the primary role of the SAFe portfolio?
To execute a set of Solutions-development activities
To hold PI Planning and execute a set of Solutions-development activities
To hold PI Planning and nurture a set of Solutions-development activities
To finance and nurture a set of Solutions-development activities
- | - | -
9 | A crosscutting Epic that spans multiple PIs is approved for implementation. What is a SAFe-recommended approach for implementation?
Trains will demonstrate their work only if they have managed to integrate and test it—if not, they can demo in the next PI
Trains will demonstrate their work related to that Epic when it’s finished
All trains and Value Streams will demonstrate their work related to the Epic at every PI boundary
- | - | -
10 | During the System Demo, it turns out that each team demonstrates their own branch of code and the system is not truly integrated. When RTE asks about the reasons behind this, the teams explain that they underestimated the integration effort and now they can't afford integration in every sprint and still accomplish the originally planned PI scope. What should the RTE suggest to the teams? | 0.167
| Integrate the existing branches and produce the System Demo; based on the amount of effort involved, make scope corrections for the remaining sprints in the PI | 1
Integrate the system in the IP sprint
Try to interate the scope of the next sprint and produce the System Demo then
- | - | -
11 | Why do we prioritize with Weighted Shortest Job First (WSJF)?
To keep our most senior business stakeholders happy and supporting SAFe adoption
Because it provides a clear ranking system
To deliver the best economic outcome from a constrained capacity system
-
12 | Which is the most accurate statement about Weighted Shortest Job First (WSJF)?
The Feature with the lowest cost of delay is sequenced first
The Feature with the highest cost of delay is sequenced first
The Feature with the lowest WSJF is sequenced first
The Feature with the highest WSJF is sequenced first
-
13 | Which SAFe Core Value best supports why teams and stakeholders attend PI Planning?
Transparency
Program execution
Built-in Quality
Alignment
14 | The analysis state of the Portfolio Kanban system has a new Epic with a completed lightweight business case. What best describes the next step for the Epic?
It will be implemented if it has the highest WSJF ranking
It will be moved to the Portfolio Backlog if it receives a “Go” decision from PPM
It will remain in the analysis state until one or more Agile Release Trains have the capacity to implement it
It will be implemented once the lightweight business case is approved by the Epic Owner
15 | Which of the following is an output from Pre- and Post-PI Planning?
Value Stream risks board
Value Stream Kanban board
ART dependencies board
Value Stream planning board
16 | Which of the following in SAFe is an example of applying cadence and synchronization?
Allocating budgets to Agile Release Trains
Creating cross-functional teams
Conducting the PI Planning Meeting
Using the Portfolio Kanban System
17 | The SAFe Principles should be implemented in sequential order rather than concurrently. | SAFe Principles
TRUE
FALSE
18 | During Pre-PI Planning, Solution Management realizes that 3 Capabilities require participation of a Supplier who has proven able to deliver but usually takes longer to coordinate and execute. Select the statement that best describes Solution Management's prioritization decisions.
Solution Management has to create a separate capacity allocation for the 3 Capabilities to avoid comparing them with the rest of the Capabilities
Solution Management will increase the time criticality component of each of these Capabilities to raise them higher in the priority list
Solution Management has to make adjustments to the denominator of the WSJF value for each of these Capabilities, as it will take longer to implement them
19 | Which of the following is NOT a step in the Portfolio Kanban?
Review
Analysis
Portfolio Backlog
Prototype
Funnel
Done
Implementation
20 | What role accepts Capabilities?
Solution Architect/Engineer
Value Stream Engineer
Solution Manager
Product Manager
21 | Value Stream Budget allocation decisions are made by ________.
Program Portfolio Management
Value Stream Engineers
Business Owners
Release Management
Solution Management
22 | The Program and Value Stream Backlogs are the short-term holding areas for ___________ and ____________.
Business Epics and Architecture Epics
Epics and Enablers
Epics and Features
Features and Capabilities
23 | What event is of highest importance in SAFe?
Scrum of Scrums
Team Demo
System Demo
Sprint planning
24 | When is the best time to release software in SAFe?
After every Iteration
Whenever the business needs it
As soon as the software meets the Solution Definition of Done
After every PI
25 | During the Inspect & Adapt, teams identified a considerable amount of action items aimed at solving their current biggest problem as a train. What is the best way for the teams to proceed?
Select a subset of items that produce a meaningful outcome in solving the problem and load them into the PI plan
Load all improvement items into the PI plan to ensure that the problem will be fully solved
Pick any one or two improvement items for the next PI
26 | Which of these Lean-Agile Principles is one of the 9 SAFe principles?
Deliver fast
Build incrementally with fast, integrated learning cycles
Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale
Agree to pursue evolutionary change
27 | The SAFe Principle “Assume variability; preserve options” enables ______________.
Better economic results
Flexibility in release dates
Stronger definition and tracking requirements
Reduction in WIP
Variability of scope but fixed Solution Context
28 | What does the program Roadmap do in SAFe?
Describes the program commitment for the current and next 2 PIs
Describes technical dependencies between Features
Provides visibility into the Portfolio Epics being implemented in the next year
Includes committed confidence and visibility for the current PI and a forecast for the next 1 or 2 PIs
30 | What period of time should the Program and Value Stream Roadmaps usually cover?
1 to 2 PIs
2 to 3 PIs
3 to 4 PIs
4 or more PIs
31 | A company is struggling to implement Agile. Management thinks the teams could do much more and doesn’t trust their estimates. What can management and teams do to bridge the trust gap?
Provide management with a detailed work breakdown structure and motivation for the estimates
Assign a liaison between management and the teams who will help manage expectations and facilitate status reporting
Involve management and teams in PI Planning
Have management estimate the work in parallel with teams
32 | Which one of the following statements about Enabler Features is true?
Future Enabler Features influence the cost of delay of current business Features
Time value is the only relevant component of cost of delay of current Enabler Features
Future business Features influence the cost of delay of current Enabler Features
Enabler Features are always less important than business Features
33 | Why is Test-First important?
User story implementation is more likely to meet the Product Owner’s acceptance criteria
There is less likelihood of defects from the implementation of a user story
The cost of implementation will likely be much lower
All of the above
34 | The goal of the Capability section of the Value Stream Kanban is to _______.
Facilitate Capability readiness
Create a Feature light-weight business case
Make funding decisions
35 | What is the recommended way to express a Feature or Capability?
Job to be done
Business use case
Feature and Benefit
User story
36 | What is the goal of Lean?
Relentless improvement
Lean-Agile leadership
Sustainable shortest lead time, best quality and value
Respect for people and culture
37 | What is the most effective way to avoid waterfalling a sprint?
By splitting Stories into smaller Stories and working on them serially
By using the first sprint of each PI as a design sprint
By deferring the Definition of Done for Stories to the IP sprint
38 | When should a crosscutting Enabler be implemented concurrently by all affected ARTs?
When overall risk is high
When cost of delay for all ARTs/Value Streams is the same
When the level of uncertainty is high
When cost of delay is unacceptably high
39 | The Team Backlog contains the Stories that the Product Owner has committed to delivering.
TRUE
FALSE
40 | At the end of PI Planning, Day 2, it turns out that one of the teams has no stretch Objectives. When asked, the team members explain that all the functionality must be completed in this PI, otherwise the organization will not comply with regulatory requirements. What would you suggest as the best way to proceed?
Leave the team's plan as is
Consider teams helping each other at the cost of reducing the original scope of work
Split the team's scope into committed and stretch Objectives, based on implementation risk
41 | In an Enterprise with one Solution portfolio and one overall Budget, the Budget is allocated to the various Value Streams and Agile Release Trains of the portfolio by the __________________.
Epic Owner(s)
Product Management Team
Program Portfolio Management Team
Economic Decision-Making Framework
42 | Who typically holds responsibility for implementing and managing the Portfolio Kanban?
Program Portfolio Management
Release Management
System Team
Product and Solution Management
43 | In what scenario would 4-level SAFe most likely be needed?
When a Value Stream can be delivered by a single ART
When Portfolio Business and Enabler Epics span multiple ARTs
When multiple ARTs are needed to accomplish the Portfolio's Strategic Themes
When a Portfolio consists of multiple ARTs and multiple customers
When a Portfolio consists of multiple Value Streams with multiple ARTs
44 | The importance of this event cannot be overstated. It is a high-profile event, and the harbinger of near-future Value Stream and portfolio investment decisions. It is the only true measure of progress, and it is the primary mitigator of investment risk for the Value Stream. What event is this?
Solution Demo
PI Demo
Sprint Demo
System Demo
45 | Business Owners assign business value to the Teams’ PI Objectives to create alignment on priorities
TRUE
FALSE
46 | What best describes how a large Value Stream releases the Solution?
Releasing happens either at the Value Stream level or at the ART level, but not at both
Releasing happens primarily at the ART level to be able to accommodate Releases dates that require sprint-level granularity, as opposed to PIs
As long as the Release process is coordinated, both the Value Stream and its trains can release
47 | Which statement best describes Architectural Runway?
Architectural Runway is a detailed plan of the system design
Architectural Runway is actual code that enables future business value
Architectural Runway describes the future architectural ideas in abstract terms
48 | Select the statement that best describes the connection between Features and Capabilities in a large Value Stream.
Some Features may not have parent Capabilities
Every Feature has a parent Capability
Some Capabilities may not have child Features
49 | What is the foundation of the SAFe House of Lean?
Relentless improvement
Innovation
Lean-Agile Leadership
Respect for people and culture
Flow
50 | How would you most simply measure average lead time in a Kanban system?
Measure the vertical distance between arrival and departure lines on a continuous flow diagram (CFD)
Measure the horizontal distance between arrival and departure lines on a continuous flow diagram (CFD)
Plot the lead times of at least 6 items on a control chart
Measure the lead time for at least 3 items and calculate the statistical mean of the items
51 | What best describes aspects of the team's commitment during PI Planning?
A team does not commit to stretch Objectives
A team commits to all Stories they put on their PI plan
A team commits to resolve all the risks identified during PI Planning
A team commits to the PI Objectives with the highest business value
52 | A single Agile Release Train can have software, firmware and hardware engineers on board.
TRUE
FALSE
53 | After what event should there be agreement on the PI Objectives to be implemented by the end of the PI and demoed at the next Solution Demo?
Portfolio Planning
Pre-PI Planning
Value Stream Planning
Post-PI Planning
54 | Feature teams are beneficial because they have less dependencies on each other than component teams.
TRUE
FALSE
55 | When is Pre-PI Planning needed?
When multiple ARTs working in the same Value Stream need to align and coordinate
When teams cannot identify and estimate Stories in PI Planning and need more time to prepare
When there is only one day to run PI Planning, so more time is needed to prepare to run it effectively
When Product Owners and Scrum Masters need to coordinate dependencies within the ART
56 | What element of the framework best realizes Principle 4 of SAFe: "Build incrementally with fast, integrated learning cycles"?
Architectural Runway
Vision
System Demo
Economic Framework